Detailed Project Report (DPR) – Final Project Plan

Project: SHE-Mart India Enterprise Retail Platform

# 1. Project Identification

| Item | Details |
| --- | --- |
| Project Name | SHE-Mart India Enterprise Retail Platform |
| Document Type | Detailed Project Report (DPR) – Implementation & Cost Plan |
| Execution Model | Turnkey implementation + Managed Hosting & Operations |
| Implementation Duration | 6 Months (24 Weeks) |
| Scale Coverage | Up to 1,500 outlets (Pan-India) |
| Maximum User Capacity | Up to 22,50,000 registered users |

# 2. Service Scope (Services to be Provided)

Program Management Services: PMO governance, milestone tracking, risk/issue management, steering reviews.

Business & Technical Documentation: BRD, SRS, HLD/LLD, API specifications, SOPs, and handover documents.

Application Development Services: backend APIs/microservices, admin portals, web platform, Android/iOS apps.

Integration Services: payment gateway, OTP/SMS, WhatsApp, email, push notifications, search and analytics.

Testing & Quality Assurance: unit, integration, system, performance, security testing and UAT support.

Cloud Hosting & Managed Operations: provisioning, deployment, monitoring, backup/DR, patching, incident handling.

Security & Compliance Services: secure configuration, logging controls, VAPT coordination and closure support.

Training & Handover: admin/user training, knowledge transfer, runbook and operational transition.

# 3. Functional Modules to be Developed

## 3.1 Core Business Modules

User onboarding, authentication, and role-based access control

Outlet onboarding and hierarchy management

Product catalog and category management

Inventory management (store and warehouse level)

Cart, checkout, and order lifecycle management

Payment orchestration and transaction status management

Settlement and payout processing

Returns and refunds workflow

Loyalty and rewards engine (D-Coins)

Notification center (SMS/WhatsApp/Email/Push)

Grievance/helpdesk and ticket workflow

Operational reports and analytics

## 3.2 Management Portals (9 Portals)

| # | Portal |
| --- | --- |
| 1 | National Admin |
| 2 | Zonal Operations |
| 3 | Regional Operations |
| 4 | Outlet Operations / POS |
| 5 | Finance & Settlement |
| 6 | Product & Merchandising |
| 7 | CRM / Support Desk |
| 8 | Marketing / Loyalty Console |
| 9 | Compliance & Audit Console |

# 4. Technology & Infrastructure Plan (Approved Baseline: Section 3 Model)

## 4.1 Infrastructure Stack

Load Balancer (ALB/Nginx) with SSL termination

Auto-scaling Application Cluster (EC2/ECS/Fargate)

RDS PostgreSQL 16 (Multi-AZ)

Redis Cache (ElastiCache)

OpenSearch

Kafka/MSK for asynchronous processing

Document database (MongoDB Atlas/DocumentDB)

Object storage (S3) + CDN (CloudFront)

CloudWatch + Grafana monitoring and alerting

WAF + baseline DDoS protections

CI/CD pipeline (GitHub Actions + CodeDeploy)

## 4.2 Monthly Infrastructure Cost (Section 3 Aligned)

| Scenario | Users/Outlet | Total Users | Infra Monthly Cost |
| --- | --- | --- | --- |
| A | 500 | 7,50,000 | ₹1.26L – ₹2.00L |
| B | 1,000 | 15,00,000 | ₹3.10L – ₹5.00L |
| C | 1,500 | 22,50,000 | ₹6.20L – ₹10.20L |

# 5. Team Size and Deployment Plan (6 Months)

Total Team Size: 14 members

| Role | Count | Duration (Months) | Monthly CTC (₹) | Sub-total (₹) |
| --- | --- | --- | --- | --- |
| Project Manager / Scrum Master | 1 | 6 | 1,20,000 | 7,20,000 |
| Backend Lead | 1 | 6 | 1,40,000 | 8,40,000 |
| Backend Developer (Sr.) | 2 | 6 | 90,000 | 10,80,000 |
| Backend Developer (Jr.) | 1 | 6 | 55,000 | 3,30,000 |
| Frontend Developer | 2 | 6 | 80,000 | 9,60,000 |
| Mobile Developer | 2 | 6 | 85,000 | 10,20,000 |
| UI/UX Designer (Sr.) | 1 | 6 | 80,000 | 4,80,000 |
| UI/UX Designer (Jr.) | 1 | 4 | 45,000 | 1,80,000 |
| QA Lead / Test Engineer | 1 | 6 | 75,000 | 4,50,000 |
| QA Engineer (Jr.) | 1 | 5 | 40,000 | 2,00,000 |
| DevOps / Cloud Engineer | 1 | 6 | 1,10,000 | 6,60,000 |
| Total Salary Cost | 14 |  |  | ₹69,20,000 |

# 6. Additional Project Costs

| Cost Item | Amount (₹) |
| --- | --- |
| Office/Remote Overheads (15% of salary) | 10,38,000 |
| Software Licenses (Figma/Jira/GitHub/Postman/Slack) | 1,20,000 |
| Dev & Staging Cloud Environment (6 months) | 1,80,000 |
| VAPT Audit (external) | 2,00,000 |
| Testing Devices (Android/iOS shared) | 80,000 |
| QA Automation Tools/Infra | 60,000 |
| App Store Fees | 10,500 |
| Contingency/Risk Buffer (5%) | 4,30,425 |
| Total Additional Cost | ₹21,18,925 |

# 7. Final Development Cost (One-time)

| Component | Amount (₹) |
| --- | --- |
| Total Salary Cost | 69,20,000 |
| Additional Project Costs | 21,18,925 |
| Base Project Cost | ₹90,38,925 |
| Agency Margin (20%) | 18,07,785 |
| Final Development Cost | ₹1,08,46,710 |

Note: Taxes/GST shall apply as per statutory rates.

# 8. Milestone-Based Payment Plan (24 Weeks, Percentage Linked)

Rule: Milestone amount = Contract Value (CV) × Milestone %.

For CV = ₹1,08,46,710, milestone values are as follows:

| Milestone | Week | % | Amount (₹) |
| --- | --- | --- | --- |
| M1 Contract Signing & Mobilization | 1 | 20% | 21,69,342 |
| M2 SRS + Architecture Sign-off | 4 | 10% | 10,84,671 |
| M3 Core Backend on Staging | 8 | 10% | 10,84,671 |
| M4 Mobile/Web Demo Acceptance | 12 | 10% | 10,84,671 |
| M5 Pilot Go-Live + Transactions | 16 | 20% | 21,69,342 |
| M6 Dashboards + Loyalty Operational | 20 | 10% | 10,84,671 |
| M7 National Rollout Completion | 23 | 10% | 10,84,671 |
| M8 Final Handover & Security Closure | 24 | 10% | 10,84,671 |
| Total |  | 100% | ₹1,08,46,710 |

# 9. Managed Hosting & Operations Cost (Agency-Hosted)

Excludes variable payment gateway MDR and delivery partner per-order charges.

| Scenario | Users/Outlet | Total Users | Monthly O&M (₹) |
| --- | --- | --- | --- |
| A | 500 | 7,50,000 | ₹5.08L – ₹8.89L |
| B | 1,000 | 15,00,000 | ₹7.66L – ₹12.88L |
| C | 1,500 | 22,50,000 | ₹13.87L – ₹25.75L |

| Scenario | Annual O&M |
| --- | --- |
| A | ₹0.61 Cr – ₹1.07 Cr |
| B | ₹0.92 Cr – ₹1.55 Cr |
| C | ₹1.66 Cr – ₹3.09 Cr |

# 10. Five-Year Plan with User Counts per Outlet

| Year | Outlets | Users/Outlet | Total Users | Scenario | Annual O&M (₹ Cr) |
| --- | --- | --- | --- | --- | --- |
| Year 1 | 1,500 | 500 | 7,50,000 | A | 0.61 – 1.07 |
| Year 2 | 1,500 | 1,000 | 15,00,000 | B | 0.92 – 1.55 |
| Year 3 | 1,500 | 1,500 | 22,50,000 | C | 1.66 – 3.09 |
| Year 4 | 1,500 | 1,500 | 22,50,000 | C | 1.66 – 3.09 |
| Year 5 | 1,500 | 1,500 | 22,50,000 | C | 1.66 – 3.09 |
| 5-Year O&M Total |  |  |  |  | 6.52 – 11.89 |

Total 5-Year Project Cost (Development + O&M):

Development: ₹1.0847 Cr

5-Year O&M: ₹6.52 Cr – ₹11.89 Cr

Grand Total (5-Year): ₹7.61 Cr – ₹12.98 Cr

# 11. 24-Week Delivery Plan

| Phase | Weeks | Key Deliverables |
| --- | --- | --- |
| Phase 1: Initiation & Freeze | 1–4 | BRD/SRS, architecture, compliance matrix, baseline plan |
| Phase 2: Build Sprint Cycle | 5–12 | Core modules, integrations, staging deployment |
| Phase 3: Hardening & Pilot | 13–20 | Performance tuning, security controls, pilot rollout |
| Phase 4: National Rollout & Closure | 21–24 | Full deployment, VAPT closure, UAT sign-off, handover |

# 12. Compliance and Enterprise Standards

Digital Personal Data Protection (DPDP) Act, 2023 compliance controls

IT Act and applicable rules

CERT-In directions (incident reporting and log readiness)

OWASP-aligned secure development controls

ISO 27001-aligned operational controls

Payment ecosystem compliance through licensed gateway partners

Annual VAPT through approved external auditor

# 13. SLA and Operational Commitments (Managed Hosting)

Platform availability target: >= 99.5% monthly

P1 incident response: within 15 minutes

P1 restoration target: within 4 hours (subject to dependency constraints)

Daily backup with periodic restore validation

Monthly performance and security reporting

Quarterly DR drill with documented evidence

# 14. Exclusions from Fixed Contract Value

Payment gateway MDR/transaction charges

Delivery partner per-order charges

Third-party fee revisions beyond baseline assumptions

Scope additions approved through formal change request process

# 15. Approval

This DPR is submitted for departmental review, administrative approval, and financial concurrence as per applicable procedures.